## Summary
WEEK | Totol working hours | Total man-days
| 764 | 95.5
W32 | 60 | 7.5
W33 | 60 | 7.5
W34 | 60 | 7.5
W35 | 60 | 7.5
W36 | 140 | 17.5
W37 | 100 | 12.5
W38 | 140 | 17.5
W39 | 144 | 18

## W32
Timesheet |  | Date
Name | Role | Monday (Aug-05) |  | Tuesday (Aug-06) |  | Wednesday (Aug-07) |  | Thursday (Aug-08) |  | Friday (Aug-09) |  | Saturday (Aug-10) |  | Sunday (Aug-11)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 1 techinal development | 8 | Sprint 1 techinal development | 8 | Sprint 1 techinal development | 8 | Sprint 1 techinal development | 8 | Sprint 1 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 1 business analysis | 4 | Sprint 1 business analysis | 4 | Sprint 1 business analysis | 4 | Sprint 1 business analysis | 4 | Sprint 1 business analysis | 4 | Break | 0 | Break | 0 | Total working hours | 60
Delivery brief summary
1 | Prepare development environment
2 | Download project source code and be familiar with it
3 | sprint 1 stories develop
4 | Analysis sprint tasks

## W33
Timesheet |  | Date
Name | Role | Monday (Aug-12) |  | Tuesday (Aug-013) |  | Wednesday (Aug-14) |  | Thursday (Aug-15) |  | Friday (Aug-016) |  | Saturday (Aug-17) |  | Sunday (Aug-18)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 1 techinal development | 8 | Sprint 1 techinal development | 8 | Sprint 1 techinal development | 8 | Sprint 1 techinal development | 8 | Sprint 1 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 1 business analysis | 4 | Sprint 1 business analysis | 4 | Sprint 1 business analysis | 4 | Sprint 1 business analysis | 4 | Sprint 1 business analysis | 4 | Break | 0 | Break | 0 | Total working hours | 60
Delivery brief summary
1 | Develop sprint 1 story card
2 | fix image upload bug
3 | spike for refactor front-end
4 | Analysis sprint tasks

## W34
Timesheet |  | Date
Name | Role | Monday (Aug-19) |  | Tuesday (Aug-020) |  | Wednesday (Aug-21) |  | Thursday (Aug-22) |  | Friday (Aug-023) |  | Saturday (Aug-24) |  | Sunday (Aug-25)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 2 techinal development | 8 | Sprint 2 techinal development | 8 | Sprint 2 techinal development | 8 | Sprint 2 techinal development | 8 | Sprint 2 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 2 business analysis | 4 | Sprint 2 business analysis | 4 | Sprint 2 business analysis | 4 | Sprint 2 business analysis | 4 | Sprint 2 business analysis | 4 | Break | 0 | Break | 0 | Total working hours | 60
Delivery brief summary
1 | Develop sprint 2 story card
2 | fix sprint 2 bugs
3 | build frontend CI/CD with yueze
4 | Analysis sprint tasks

## w35
Timesheet |  | Date
Name | Role | Monday (Aug-26) |  | Tuesday (Aug-27) |  | Wednesday (Aug-28) |  | Thursday (Aug-29) |  | Friday (Aug-30) |  | Saturday (Aug-31) |  | Sunday (Sep-01)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 2 techinal development | 8 | Sprint 2 techinal development | 8 | Sprint 2 techinal development | 8 | Sprint 2 techinal development | 8 | Sprint 2 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 2 business analysis | 4 | Sprint 2 business analysis | 4 | Sprint 2 business analysis | 4 | Sprint 2 business analysis | 4 | Sprint 2 business analysis | 4 | Break | 0 | Break | 0 | Total working hours | 60
Delivery brief summary
1 | Develop sprint 2 story card
2 | modify UI buttons color
3 | build frontend CI/CD with yueze
4 | Analysis sprint tasks

## W36
Timesheet |  | Date
Name | Role | Monday (Sep-02) |  | Tuesday (Sep-03) |  | Wednesday (Sep-04) |  | Thursday (Sep-05) |  | Friday (Sep-06) |  | Saturday (Sep-07) |  | Sunday (Sep-08)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 3 business analysis | 4 | Sprint 3 business analysis | 4 | Sprint 3 business analysis | 4 | Sprint 3 business analysis | 4 | Sprint 3 business analysis | 4 | Break | 0 | Break | 0
Cao Xiaoqi | DEV | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Break | 0 | Break | 0
Chen Pei | QA | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Break | 0 | Break | 0 | Total working hours | 140
Delivery brief summary
1 | Develop sprint 3 story card
2 | Prepare backend develop environment
3 | Build QA environment
4 | Analysis sprint tasks

## W37
Timesheet |  | Date
Name | Role | Monday (Sep-09) |  | Tuesday (Sep-10) |  | Wednesday (Sep-11) |  | Thursday (Sep-12) |  | Friday (Sep-13) |  | Saturday (Sep-14) |  | Sunday (Sep-15)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 4 | Sprint 3 techinal development | 0 | Sprint 3 techinal development | 0 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 3 business analysis | 4 | Sprint 3 business analysis | 4 | Sprint 3 business analysis | 4 | Sprint 3 business analysis | 4 | Sprint 3 business analysis | 0 | Break | 0 | Break | 0
Cao Xiaoqi | DEV | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 0 | Break | 0 | Break | 0
Chen Pei | QA | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 0 | Break | 0 | Break | 0 | Total working hours | 100
Delivery brief summary
1 | Develop sprint 3 frontend story card
2 | Develop sprint 3 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W38
Timesheet |  | Date
Name | Role | Monday (Sep-16) |  | Tuesday (Sep-17) |  | Wednesday (Sep-18) |  | Thursday (Sep-19) |  | Friday (Sep-20) |  | Saturday (Sep-21) |  | Sunday (Sep-22)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 4 business analysis | 4 | Sprint 4 business analysis | 4 | Sprint 4 business analysis | 4 | Sprint 4 business analysis | 4 | Sprint 4 business analysis | 4 | Break | 0 | Break | 0
Cao Xiaoqi | DEV | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Break | 0 | Break | 0
Chen Pei | QA | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Break | 0 | Break | 0 | Total working hours | 140
Delivery brief summary
1 | Develop sprint 4 frontend story card
2 | Develop sprint 4 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W39
Timesheet |  | Date
Name | Role | Monday (Sep-23) |  | Tuesday (Sep-24) |  | Wednesday (Sep-25) |  | Thursday (Sep-26) |  | Friday (Sep-27) |  | Saturday (Sep-28) |  | Sunday (Sep-29)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Break | 0 | Sprint 4 techinal development | 8
Wang Dongxue | BA | Sprint 4 business analysis | 4 | Sprint 4 business analysis | 0 | Sprint 4 business analysis | 4 | Sprint 4 business analysis | 0 | Sprint 4 business analysis | 0 | Break | 0 | Break | 0
Cao Xiaoqi | DEV | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Break | 0 | Break | 0
Chen Pei | QA | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Break | 0 | Sprint 4 techinal development | 8 | Total working hours | 144
Delivery brief summary
1 | Develop sprint 4 frontend story card
2 | Develop sprint 4 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W40
Timesheet |  | Date
Name | Role | Monday (Sep-30) |  | Tuesday (Oct-01) |  | Wednesday (Oct-02) |  | Thursday (Oct-03) |  | Friday (Oct-04) |  | Saturday (Oct-05) |  | Sunday (Oct-06)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 4 techinal development | 8 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 4 business analysis | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0
Cao Xiaoqi | DEV | Sprint 4 techinal development | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0
Chen Pei | QA | Sprint 4 techinal development | 8 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Total working hours | 16
Delivery brief summary
1 | Develop sprint 4 frontend story card
2 | Develop sprint 4 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W41
Timesheet |  | Date
Name | Role | Monday (Oct-7) |  | Tuesday (Oct-8) |  | Wednesday (Oct-9) |  | Thursday (Oct-10) |  | Friday (Oct-11) |  | Saturday (Oct-12) |  | Sunday (Oct-13)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Break | 0 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Break | 0
Wang Dongxue | BA | Break | 0 | Sprint 5 business analysis | 4 | Sprint 5 business analysis | 4 | Sprint 5 business analysis | 4 | Sprint 5 business analysis | 4 | Break | 0 | Break | 0
Cao Xiaoqi | DEV | Break | 0 | Break | 0 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Break | 0
Chen Pei | QA | Break | 0 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Break | 0 | Total working hours | 128
Delivery brief summary
1 | Develop sprint 5 frontend story card
2 | Develop sprint 5 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W42
Timesheet |  | Date
Name | Role | Monday (Oct-14) |  | Tuesday (Oct-15) |  | Wednesday (Oct-16) |  | Thursday (Oct-17) |  | Friday (Oct-18) |  | Saturday (Oct-19) |  | Sunday (Oct-20)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 5 business analysis | 4 | Sprint 5 business analysis | 4 | Sprint 5 business analysis | 4 | Sprint 5 business analysis | 4 | Sprint 5 business analysis | 4 | Break | 0 | Break | 0
Cao Xiaoqi | DEV | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Break | 0 | Break | 0
Chen Pei | QA | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Break | 0 | Break | 0 | Total working hours | 140
Delivery brief summary
1 | Develop sprint 5 frontend story card
2 | Develop sprint 5 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W43
Timesheet |  | Date
Name | Role | Monday (Oct-21) |  | Tuesday (Oct-22) |  | Wednesday (Oct-23) |  | Thursday (Oct-24) |  | Friday (Oct-25) |  | Saturday (Oct-26) |  | Sunday (Oct-27)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 5 techinal development | 4 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 5 business analysis | 4 | Sprint 5 business analysis | 4 | Sprint 5 business analysis | 4 | Sprint 5 business analysis | 4 | Sprint 5 business analysis | 4 | Break | 0 | Break | 0
Cao Xiaoqi | DEV | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Break | 0 | Break | 0
Chen Pei | QA | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Break | 0 | Break | 0 | Total working hours | 176
Delivery brief summary
1 | Develop sprint 5 frontend story card
2 | Develop sprint 5 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W44
Timesheet |  | Date
Name | Role | Monday (Oct-28) |  | Tuesday (Oct-29) |  | Wednesday (Oct-30) |  | Thursday (Oct-31) |  | Friday (Nov-1) |  | Saturday (Nov-2) |  | Sunday (Nov-3)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 6 business analysis | 4 | Break | 0 | Sprint 6 business analysis | 4 | Sprint 6 business analysis | 4 | Sprint 6 business analysis | 4 | Break | 0 | Break | 0
Cao Xiaoqi | DEV | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 4 | Break | 0
Liu Yue | QA | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Break | 0 | Break | 0 | Total working hours | 140
Delivery brief summary
1 | Develop sprint 6 frontend story card
2 | Develop sprint 6 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W45
Timesheet |  | Date
Name | Role | Monday (Nov-4) |  | Tuesday (Nov-5) |  | Wednesday (Nov-6) |  | Thursday (Nov-7) |  | Friday (Nov-8) |  | Saturday (Nov-9) |  | Sunday (Nov-10)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 16 | Sprint 6 techinal development | 4 | Break | 0
Wang Dongxue | BA | Sprint 6 business analysis | 4 | Sprint 6 business analysis | 4 | Sprint 6 business analysis | 4 | Sprint 6 business analysis | 4 | Sprint 6 business analysis | 4 | Break | 0 | Break | 0
Cao Xiaoqi | DEV | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 4 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 16 | Sprint 6 techinal development | 4 | Break | 0
Liu Yue | QA | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Break | 0 | Break | 0 | Total working hours | 160
Delivery brief summary
1 | Develop sprint 6 frontend story card
2 | Develop sprint 6 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W46
Timesheet |  | Date
Name | Role | Monday (Nov-11) |  | Tuesday (Nov-12) |  | Wednesday (Nov-13) |  | Thursday (Nov-14) |  | Friday (Nov-15) |  | Saturday (Nov-16) |  | Sunday (Nov-17)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 7 business analysis | 4 | Sprint 7 business analysis | 4 | Sprint 7 business analysis | 4 | Sprint 7 business analysis | 2 | Break | 0 | Break | 0 | Break | 0
Cao Xiaoqi | DEV | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Break | 0 | Sprint 7 techinal development | 8 | Break | 0 | Break | 0 | Total working hours | 126
Delivery brief summary
1 | Develop sprint 7 frontend story card
2 | Develop sprint 7 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W47
Timesheet |  | Date
Name | Role | Monday (Nov-18) |  | Tuesday (Nov-19) |  | Wednesday (Nov-20) |  | Thursday (Nov-21) |  | Friday (Nov-22) |  | Saturday (Nov-23) |  | Sunday (Nov-24)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Break | 0 | Sprint 7 business analysis | 2 | Sprint 7 business analysis | 4 | Sprint 7 business analysis | 4 | Sprint 7 business analysis | 4 | Break | 0 | Break | 0
Cao Xiaoqi | DEV | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 4 | Break | 0 | Total working hours | 138
Delivery brief summary
1 | Develop sprint 7 frontend story card
2 | Develop sprint 7 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W48
Timesheet |  | Date
Name | Role | Monday (Nov-25) |  | Tuesday (Nov-26) |  | Wednesday (Nov-27) |  | Thursday (Nov-28) |  | Friday (Nov-29) |  | Saturday (Nov-30) |  | Sunday (Dec-1)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 8 business analysis | 4 | Sprint 8 business analysis | 4 | Break | 0 | Break | 0 | Sprint 8 business analysis | 4 | Break | 0 | Break | 0
Cao Xiaoqi | DEV | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Break | 0 | Break | 0 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 8 business analysis | 8 | Sprint 8 business analysis | 8 | Sprint 8 business analysis | 8 | Sprint 8 business analysis | 8 | Break | 0 | Break | 0 | Break | 0 | Total working hours | 148
Delivery brief summary
1 | Develop sprint 8 frontend story card
2 | Develop sprint 8 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W49
Timesheet |  | Date
Name | Role | Monday (Dec-2) |  | Tuesday (Dec-3) |  | Wednesday (Dec-4) |  | Thursday (Dec-5) |  | Friday (Dec-6) |  | Saturday (Dec-7) |  | Sunday (Dec-8)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 8 business analysis | 4 | Sprint 8 business analysis | 4 | Sprint 8 business analysis | 4 | Sprint 8 business analysis | 2 | Sprint 8 business analysis | 4 | Break | 0 | Break | 0
Cao Xiaoqi | DEV | Break | 0 | Break | 0 | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 8 business analysis | 8 | Sprint 8 business analysis | 8 | Sprint 8 business analysis | 8 | Sprint 8 business analysis | 8 | Sprint 8 business analysis | 8 | Break | 0 | Break | 0 | Total working hours | 162
Delivery brief summary
1 | Develop sprint 8 frontend story card
2 | Develop sprint 8 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W50
Timesheet |  | Date
Name | Role | Monday (Dec-9) |  | Tuesday (Dec-10) |  | Wednesday (Dec-11) |  | Thursday (Dec-12) |  | Friday (Dec-13) |  | Saturday (Dec-14) |  | Sunday (Dec-15)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Break | 0 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 9 business analysis | 4 | Sprint 9 business analysis | 4 | Sprint 9 business analysis | 4 | Sprint 9 business analysis | 4 | Sprint 9 business analysis | 4 | Break | 0 | Break | 0
Cao Xiaoqi | Dev | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Break | 0 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Break | 0 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 9 business analysis | 8 | Sprint 9 business analysis | 8 | Sprint 9 business analysis | 8 | Sprint 9 business analysis | 8 | Sprint 9 business analysis | 8 | Break | 0 | Break | 0 | Total working hours | 156
Delivery brief summary
1 | Develop sprint 9 frontend story card
2 | Develop sprint 9 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W51
Timesheet |  | Date
Name | Role | Monday (Dec-16) |  | Tuesday (Dec-17) |  | Wednesday (Dec-18) |  | Thursday (Dec-19) |  | Friday (Dec-20) |  | Saturday (Dec-21) |  | Sunday (Dec-22)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 9 business analysis | 4 | Sprint 9 business analysis | 4 | Sprint 9 business analysis | 4 | Break | 0 | Sprint 9 business analysis | 4 | Break | 0 | Break | 0
Cao Xiaoqi | Dev | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 9 business analysis | 8 | Sprint 9 business analysis | 8 | Sprint 9 business analysis | 8 | Sprint 9 business analysis | 8 | Sprint 9 business analysis | 8 | Break | 0 | Break | 0 | Total working hours | 176
Delivery brief summary
1 | Develop sprint 9 frontend story card
2 | Develop sprint 9 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W52
Timesheet |  | Date
Name | Role | Monday (Dec-23) |  | Tuesday (Dec-24) |  | Wednesday (Dec-25) |  | Thursday (Dec-26) |  | Friday (Dec-27) |  | Saturday (Dec-28) |  | Sunday (Dec-29)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 10 techinal development | 8 | Sprint 10 techinal development | 8 | Sprint 10 techinal development | 8 | Sprint 10 techinal development | 8 | Sprint 10 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 10 business analysis | 4 | Sprint 10 business analysis | 4 | Sprint 10 business analysis | 4 | Sprint 10 business analysis | 4 | Break | 0 | Break | 0 | Break | 0
Cao Xiaoqi | Dev | Sprint 10 techinal development | 8 | Sprint 10 techinal development | 8 | Sprint 10 techinal development | 8 | Sprint 10 techinal development | 8 | Sprint 10 techinal development | 8 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 10 techinal development | 8 | Break | 0 | Sprint 10 techinal development | 8 | Sprint 10 techinal development | 8 | Sprint 10 techinal development | 8 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 10 business analysis | 8 | Sprint 10 business analysis | 8 | Sprint 10 business analysis | 8 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Total working hours | 152
Delivery brief summary
1 | Develop sprint 10 frontend story card
2 | Develop sprint 10 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W53
Timesheet |  | Date
Name | Role | Monday (Dec-30) |  | Tuesday (Dec-31) |  | Wednesday (Jan-1) |  | Thursday (Jan-2) |  | Friday (Jan-3) |  | Saturday (Jan-4) |  | Sunday (Jan-5)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 10 techinal development | 8 | Sprint 10 techinal development | 8 | Break | 0 | Sprint 10 techinal development | 8 | Sprint 10 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Break | 0 | Break | 0 | Break | 0 | Sprint 10 business analysis | 4 | Sprint 10 business analysis | 4 | Break | 0 | Break | 0
Cao Xiaoqi | Dev | Sprint 10 techinal development | 8 | Sprint 10 techinal development | 8 | Break | 0 | Sprint 10 techinal development | 8 | Sprint 10 techinal development | 4 | Break | 0 | Break | 0
Liu Yue | QA | Break | 0 | Break | 0 | Break | 0 | Sprint 10 techinal development | 8 | Sprint 10 techinal development | 8 | Break | 0 | Break | 0
Huang Xinyu | BA | Break | 0 | Break | 0 | Break | 0 | Sprint 10 business analysis | 8 | Sprint 10 business analysis | 8 | Break | 0 | Break | 0 | Total working hours | 100
Delivery brief summary
1 | Develop sprint 10 frontend story card
2 | Develop sprint 10 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W54
Timesheet |  | Date
Name | Role | Monday (Jan-6) |  | Tuesday (Jan-7) |  | Wednesday (Jan-8) |  | Thursday (Jan-9) |  | Friday (Jan-10) |  | Saturday (Jan-11) |  | Sunday (Jan-12)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 11 techinal development | 8 | Sprint 11 techinal development | 8 | Sprint 11 techinal development | 8 | Sprint 11 techinal development | 8 | Sprint 11 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 11 business analysis | 4 | Sprint 11 business analysis | 2 | Sprint 11 business analysis | 4 | Sprint 11 business analysis | 4 | Sprint 11 business analysis | 4 | Break | 0 | Break | 0
Cao Xiaoqi | Dev | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 11 techinal development | 8 | Sprint 11 techinal development | 8 | Sprint 11 techinal development | 8 | Sprint 11 techinal development | 8 | Sprint 11 techinal development | 8 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 11 business analysis | 8 | Sprint 11 business analysis | 8 | Sprint 11 business analysis | 8 | Sprint 11 business analysis | 8 | Sprint 11 business analysis | 8 | Break | 0 | Break | 0 | Total working hours | 138
Delivery brief summary
1 | Develop sprint 11 frontend story card
2 | Develop sprint 11 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W55
Timesheet |  | Date
Name | Role | Monday (Jan-13) |  | Tuesday (Jan-14) |  | Wednesday (Jan-15) |  | Thursday (Jan-16) |  | Friday (Jan-17) |  | Saturday (Jan-18) |  | Sunday (Jan-19)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 11 techinal development | 8 | Sprint 11 techinal development | 8 | Sprint 11 techinal development | 8 | Sprint 11 techinal development | 8 | Sprint 11 techinal development | 8 | Break | 0 | Sprint 11 techinal development | 8
Wang Dongxue | BA | Sprint 11 business analysis | 4 | Sprint 11 business analysis | 4 | Sprint 11 business analysis | 4 | Sprint 11 business analysis | 4 | Sprint 11 business analysis | 4 | Break | 0 | Sprint 11 business analysis | 4
Cao Xiaoqi | Dev | Sprint 11 techinal development | 8 | Sprint 11 techinal development | 8 | Sprint 11 techinal development | 8 | Sprint 11 techinal development | 8 | Sprint 11 techinal development | 8 | Break | 0 | Sprint 11 techinal development | 8
Liu Yue | QA | Sprint 11 techinal development | 8 | Sprint 11 techinal development | 8 | Sprint 11 techinal development | 8 | Sprint 11 techinal development | 8 | Sprint 11 techinal development | 8 | Break | 0 | Sprint 11 techinal development | 8
Huang Xinyu | BA | Sprint 11 business analysis | 8 | Sprint 11 business analysis | 8 | Sprint 11 business analysis | 8 | Sprint 11 business analysis | 8 | Sprint 11 business analysis | 8 | Break | 0 | Sprint 11 business analysis | 8 | Total working hours | 216
Delivery brief summary
1 | Develop sprint 11 frontend story card
2 | Develop sprint 11 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W56
Timesheet |  | Date
Name | Role | Monday (Jan-20) |  | Tuesday (Jan-21) |  | Wednesday (Jan-22) |  | Thursday (Jan-23) |  | Friday (Jan-24) |  | Saturday (Jan-25) |  | Sunday (Jan-26)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 11 techinal development | 8 | Sprint 11 techinal development | 8 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 11 business analysis | 4 | Sprint 11 business analysis | 2 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0
Cao Xiaoqi | Dev | Sprint 11 techinal development | 8 | Sprint 11 techinal development | 8 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 11 techinal development | 8 | Sprint 11 techinal development | 8 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 11 business analysis | 8 | Sprint 11 business analysis | 8 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Total working hours | 70
Delivery brief summary
1 | Develop sprint 11 frontend story card
2 | Develop sprint 11 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W57
Timesheet |  | Date
Name | Role | Monday (Jan-27) |  | Tuesday (Jan-28) |  | Wednesday (Jan-29) |  | Thursday (Jan-30) |  | Friday (Jan-31) |  | Saturday (Feb-1) |  | Sunday (Feb-2)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0
Wang Dongxue | BA | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0
Cao Xiaoqi | Dev | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0
Liu Yue | QA | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0
Huang Xinyu | BA | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Total working hours | 0
Delivery brief summary
1 | Develop sprint 0 frontend story card
2 | Develop sprint 0 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W58
Timesheet |  | Date
Name | Role | Monday (Feb-3) |  | Tuesday (Feb-4) |  | Wednesday (Feb-5) |  | Thursday (Feb-6) |  | Friday (Feb-7) |  | Saturday (Feb-8) |  | Sunday (Feb-9)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 12 techinal development | 8 | Sprint 12 techinal development | 8 | Sprint 12 techinal development | 8 | Sprint 12 techinal development | 8 | Sprint 12 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 12 business analysis | 4 | Sprint 12 business analysis | 4 | Sprint 12 business analysis | 4 | Sprint 12 business analysis | 4 | Sprint 12 business analysis | 4 | Break | 0 | Break | 0
Cao Xiaoqi | Dev | Sprint 12 techinal development | 8 | Sprint 12 techinal development | 8 | Sprint 12 techinal development | 8 | Sprint 12 techinal development | 8 | Sprint 12 techinal development | 8 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 12 techinal development | 8 | Sprint 12 techinal development | 8 | Sprint 12 techinal development | 8 | Break | 0 | Sprint 12 techinal development | 8 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 12 business analysis | 8 | Sprint 12 business analysis | 8 | Sprint 12 business analysis | 8 | Sprint 12 business analysis | 8 | Sprint 12 business analysis | 8 | Break | 0 | Break | 0 | Total working hours | 172
Delivery brief summary
1 | Develop sprint 12 frontend story card
2 | Develop sprint 12 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W59
Timesheet |  | Date
Name | Role | Monday (Feb-10) |  | Tuesday (Feb-11) |  | Wednesday (Feb-12) |  | Thursday (Feb-13) |  | Friday (Feb-14) |  | Saturday (Feb-15) |  | Sunday (Feb-16)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 12 techinal development | 8 | Sprint 12 techinal development | 8 | Sprint 12 techinal development | 8 | Sprint 12 techinal development | 8 | Sprint 12 techinal development | 8 | Break | 0 | Break | 0
Cao Xiaoqi | Dev | Sprint 12 techinal development | 8 | Sprint 12 techinal development | 8 | Sprint 12 techinal development | 8 | Sprint 12 techinal development | 8 | Sprint 12 techinal development | 8 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 12 techinal development | 8 | Sprint 12 techinal development | 8 | Sprint 12 techinal development | 8 | Sprint 12 techinal development | 8 | Sprint 12 techinal development | 8 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 12 business analysis | 8 | Sprint 12 business analysis | 8 | Sprint 12 business analysis | 8 | Sprint 12 business analysis | 8 | Sprint 12 business analysis | 8 | Break | 0 | Break | 0 | Total working hours | 160
Delivery brief summary
1 | Develop sprint 12 frontend story card
2 | Develop sprint 12 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W60
Timesheet |  | Date
Name | Role | Monday (Feb-17) |  | Tuesday (Feb-18) |  | Wednesday (Feb-19) |  | Thursday (Feb-20) |  | Friday (Feb-21) |  | Saturday (Feb-22) |  | Sunday (Feb-23)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 13 techinal development | 8 | Sprint 13 techinal development | 8 | Sprint 13 techinal development | 8 | Sprint 13 techinal development | 8 | Sprint 13 techinal development | 8 | Break | 0 | Break | 0
Cao Xiaoqi | Dev | Sprint 13 techinal development | 8 | Sprint 13 techinal development | 8 | Sprint 13 techinal development | 8 | Sprint 13 techinal development | 8 | Sprint 13 techinal development | 8 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 13 techinal development | 8 | Sprint 13 techinal development | 8 | Sprint 13 techinal development | 8 | Sprint 13 techinal development | 8 | Sprint 13 techinal development | 8 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 13 business analysis | 8 | Sprint 13 business analysis | 8 | Sprint 13 business analysis | 8 | Sprint 13 business analysis | 8 | Sprint 13 business analysis | 8 | Break | 0 | Break | 0 | Total working hours | 160
Delivery brief summary
1 | Develop sprint 13 frontend story card
2 | Develop sprint 13 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W61
Timesheet |  | Date
Name | Role | Monday (Feb-24) |  | Tuesday (Feb-25) |  | Wednesday (Feb-26) |  | Thursday (Feb-27) |  | Friday (Feb-28) |  | Saturday (Feb-29) |  | Sunday (Mar-1)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 13 techinal development | 8 | Sprint 13 techinal development | 8 | Sprint 13 techinal development | 8 | Sprint 13 techinal development | 8 | Sprint 13 techinal development | 8 | Break | 0 | Break | 0
Cao Xiaoqi | Dev | Sprint 13 techinal development | 8 | Sprint 13 techinal development | 8 | Sprint 13 techinal development | 8 | Sprint 13 techinal development | 8 | Sprint 13 techinal development | 8 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 13 techinal development | 8 | Sprint 13 techinal development | 8 | Sprint 13 techinal development | 8 | Sprint 13 techinal development | 8 | Sprint 13 techinal development | 8 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 13 business analysis | 8 | Sprint 13 business analysis | 8 | Sprint 13 business analysis | 8 | Sprint 13 business analysis | 8 | Sprint 13 business analysis | 8 | Break | 0 | Break | 0 | Total working hours | 160
Delivery brief summary
1 | Develop sprint 13 frontend story card
2 | Develop sprint 13 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W62
Timesheet |  | Date
Name | Role | Monday (Mar-2) |  | Tuesday (Mar-3) |  | Wednesday (Mar-4) |  | Thursday (Mar-5) |  | Friday (Mar-6) |  | Saturday (Mar-7) |  | Sunday (Mar-8)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 14 techinal development | 8 | Sprint 14 techinal development | 8 | Sprint 14 techinal development | 8 | Sprint 14 techinal development | 8 | Sprint 14 techinal development | 8 | Break | 0 | Break | 0
Cao Xiaoqi | Dev | Sprint 14 techinal development | 8 | Sprint 14 techinal development | 8 | Sprint 14 techinal development | 8 | Sprint 14 techinal development | 8 | Sprint 14 techinal development | 8 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 14 techinal development | 8 | Sprint 14 techinal development | 8 | Sprint 14 techinal development | 8 | Break | 0 | Break | 0 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 14 business analysis | 8 | Sprint 14 business analysis | 8 | Sprint 14 business analysis | 8 | Sprint 14 business analysis | 8 | Sprint 14 business analysis | 8 | Break | 0 | Break | 0 | Total working hours | 144
Delivery brief summary
1 | Develop sprint 14 frontend story card
2 | Develop sprint 14 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W63
Timesheet |  | Date
Name | Role | Monday (Mar-9) |  | Tuesday (Mar-10) |  | Wednesday (Mar-11) |  | Thursday (Mar-12) |  | Friday (Mar-13) |  | Saturday (Mar-14) |  | Sunday (Mar-15)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 14 techinal development | 8 | Sprint 14 techinal development | 8 | Sprint 14 techinal development | 8 | Sprint 14 techinal development | 8 | Sprint 14 techinal development | 8 | Break | 0 | Break | 0
Cao Xiaoqi | Dev | Sprint 14 techinal development | 8 | Sprint 14 techinal development | 8 | Sprint 14 techinal development | 8 | Sprint 14 techinal development | 8 | Sprint 14 techinal development | 8 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 14 techinal development | 8 | Sprint 14 techinal development | 8 | Sprint 14 techinal development | 8 | Sprint 14 techinal development | 8 | Sprint 14 techinal development | 8 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 14 business analysis | 8 | Sprint 14 business analysis | 8 | Sprint 14 business analysis | 8 | Sprint 14 business analysis | 8 | Sprint 14 business analysis | 8 | Break | 0 | Break | 0 | Total working hours | 160
Delivery brief summary
1 | Develop sprint 14 frontend story card
2 | Develop sprint 14 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W64
Timesheet |  | Date
Name | Role | Monday (Mar-16) |  | Tuesday (Mar-17) |  | Wednesday (Mar-18) |  | Thursday (Mar-19) |  | Friday (Mar-20) |  | Saturday (Mar-21) |  | Sunday (Mar-22)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 15 techinal development | 8 | Sprint 15 techinal development | 8 | Sprint 15 techinal development | 8 | Sprint 15 techinal development | 8 | Sprint 15 techinal development | 8 | Break | 0 | Break | 0
Cao Xiaoqi | Dev | Sprint 15 techinal development | 8 | Sprint 15 techinal development | 8 | Sprint 15 techinal development | 8 | Sprint 15 techinal development | 8 | Sprint 15 techinal development | 8 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 15 techinal development | 8 | Sprint 15 techinal development | 8 | Sprint 15 techinal development | 8 | Sprint 15 techinal development | 8 | Sprint 15 techinal development | 8 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 15 business analysis | 8 | Sprint 15 business analysis | 8 | Sprint 15 business analysis | 8 | Sprint 15 business analysis | 8 | Sprint 15 business analysis | 8 | Break | 0 | Break | 0 | Total working hours | 160
Delivery brief summary
1 | Develop sprint 15 frontend story card
2 | Develop sprint 15 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W65
Timesheet |  | Date
Name | Role | Monday (Mar-23) |  | Tuesday (Mar-24) |  | Wednesday (Mar-25) |  | Thursday (Mar-26) |  | Friday (Mar-27) |  | Saturday (Mar-28) |  | Sunday (Mar-29)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 15 techinal development | 8 | Sprint 15 techinal development | 8 | Sprint 15 techinal development | 8 | Sprint 15 techinal development | 8 | Sprint 15 techinal development | 8 | Break | 0 | Break | 0
Cao Xiaoqi | Dev | Sprint 15 techinal development | 4 | Sprint 15 techinal development | 4 | Sprint 15 techinal development | 8 | Sprint 15 techinal development | 8 | Sprint 15 techinal development | 8 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 15 techinal development | 8 | Sprint 15 techinal development | 8 | Sprint 15 techinal development | 8 | Sprint 15 techinal development | 8 | Sprint 15 techinal development | 8 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 15 business analysis | 8 | Sprint 15 business analysis | 8 | Sprint 15 business analysis | 8 | Sprint 15 business analysis | 8 | Sprint 15 business analysis | 8 | Break | 0 | Break | 0 | Total working hours | 152
Delivery brief summary
1 | Develop sprint 15 frontend story card
2 | Develop sprint 15 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W66
Timesheet |  | Date
Name | Role | Monday (Mar-30) |  | Tuesday (Mar-31) |  | Wednesday (Apr-1) |  | Thursday (Apr-2) |  | Friday (Apr-3) |  | Saturday (Apr-4) |  | Sunday (Apr-5)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 16 techinal development | 8 | Sprint 16 techinal development | 8 | Sprint 16 techinal development | 8 | Sprint 16 techinal development | 8 | Sprint 16 techinal development | 8 | Break | 0 | Break | 0
Cao Xiaoqi | Dev | Sprint 16 techinal development | 8 | Sprint 16 techinal development | 8 | Sprint 16 techinal development | 8 | Sprint 16 techinal development | 8 | Sprint 16 techinal development | 8 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 16 techinal development | 8 | Sprint 16 techinal development | 8 | Sprint 16 techinal development | 8 | Sprint 16 techinal development | 8 | Break | 0 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 16 business analysis | 8 | Sprint 16 business analysis | 8 | Sprint 16 business analysis | 8 | Sprint 16 business analysis | 8 | Sprint 16 business analysis | 8 | Break | 0 | Break | 0 | Total working hours | 152
Delivery brief summary
1 | Develop sprint 16 frontend story card
2 | Develop sprint 16 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W67
Timesheet |  | Date
Name | Role | Monday (Apr-6) |  | Tuesday (Apr-7) |  | Wednesday (Apr-8) |  | Thursday (Apr-9) |  | Friday (Apr-10) |  | Saturday (Apr-11) |  | Sunday (Apr-12)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 16 techinal development | 8 | Sprint 16 techinal development | 8 | Sprint 16 techinal development | 8 | Sprint 16 techinal development | 8 | Sprint 16 techinal development | 8 | Break | 0 | Break | 0
Cao Xiaoqi | Dev | Sprint 16 techinal development | 8 | Sprint 16 techinal development | 8 | Sprint 16 techinal development | 8 | Sprint 16 techinal development | 8 | Sprint 16 techinal development | 8 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 16 techinal development | 8 | Sprint 16 techinal development | 8 | Sprint 16 techinal development | 8 | Sprint 16 techinal development | 8 | Sprint 16 techinal development | 8 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 16 business analysis | 8 | Sprint 16 business analysis | 8 | Sprint 16 business analysis | 8 | Sprint 16 business analysis | 8 | Sprint 16 business analysis | 8 | Break | 0 | Break | 0 | Total working hours | 160
Delivery brief summary
1 | Develop sprint 16 frontend story card
2 | Develop sprint 16 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W68
Timesheet |  | Date
Name | Role | Monday (Apr-13) |  | Tuesday (Apr-14) |  | Wednesday (Apr-15) |  | Thursday (Apr-16) |  | Friday (Apr-17) |  | Saturday (Apr-18) |  | Sunday (Apr-19)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 17 techinal development | 8 | Sprint 17 techinal development | 8 | Sprint 17 techinal development | 8 | Sprint 17 techinal development | 8 | Sprint 17 techinal development | 8 | Break | 0 | Break | 0
Cao Xiaoqi | Dev | Sprint 17 techinal development | 8 | Sprint 17 techinal development | 8 | Sprint 17 techinal development | 8 | Sprint 17 techinal development | 8 | Sprint 17 techinal development | 8 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 17 techinal development | 8 | Sprint 17 techinal development | 8 | Sprint 17 techinal development | 8 | Sprint 17 techinal development | 8 | Sprint 17 techinal development | 8 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 17 business analysis | 8 | Sprint 17 business analysis | 8 | Sprint 17 business analysis | 8 | Sprint 17 business analysis | 8 | Sprint 17 business analysis | 8 | Break | 0 | Break | 0 | Total working hours | 160
Delivery brief summary
1 | Develop sprint 17 frontend story card
2 | Develop sprint 17 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W69
Timesheet |  | Date
Name | Role | Monday (Apr-20) |  | Tuesday (Apr-21) |  | Wednesday (Apr-22) |  | Thursday (Apr-23) |  | Friday (Apr-24) |  | Saturday (Apr-25) |  | Sunday (Apr-26)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 17 techinal development | 8 | Sprint 17 techinal development | 8 | Sprint 17 techinal development | 8 | Sprint 17 techinal development | 8 | Sprint 17 techinal development | 8 | Break | 0 | Sprint 17 techinal development | 8
Cao Xiaoqi | Dev | Sprint 17 techinal development | 8 | Sprint 17 techinal development | 8 | Sprint 17 techinal development | 8 | Sprint 17 techinal development | 8 | Sprint 17 techinal development | 8 | Break | 0 | Sprint 17 techinal development | 8
Liu Yue | QA | Sprint 17 techinal development | 8 | Sprint 17 techinal development | 8 | Sprint 17 techinal development | 8 | Sprint 17 techinal development | 8 | Sprint 17 techinal development | 8 | Break | 0 | Sprint 17 techinal development | 8
Huang Xinyu | BA | Sprint 17 business analysis | 8 | Sprint 17 business analysis | 8 | Sprint 17 business analysis | 8 | Sprint 17 business analysis | 8 | Sprint 17 business analysis | 8 | Break | 0 | Sprint 17 business analysis | 8 | Total working hours | 192
Delivery brief summary
1 | Develop sprint 17 frontend story card
2 | Develop sprint 17 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W70
Timesheet |  | Date
Name | Role | Monday (Apr-27) |  | Tuesday (Apr-28) |  | Wednesday (Apr-29) |  | Thursday (Apr-30) |  | Friday (May-1) |  | Saturday (May-2) |  | Sunday (May-3)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 18 techinal development | 8 | Sprint 18 techinal development | 8 | Sprint 18 techinal development | 4 | Sprint 18 techinal development | 8 | Break | 0 | Break | 0 | Break | 0
Cao Xiaoqi | Dev | Sprint 18 techinal development | 8 | Sprint 18 techinal development | 8 | Sprint 18 techinal development | 8 | Sprint 18 techinal development | 8 | Break | 0 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 18 techinal development | 8 | Sprint 18 techinal development | 8 | Sprint 18 techinal development | 8 | Sprint 18 techinal development | 8 | Break | 0 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 18 business analysis | 8 | Sprint 18 business analysis | 8 | Sprint 18 business analysis | 8 | Sprint 18 business analysis | 8 | Break | 0 | Break | 0 | Break | 0 | Total working hours | 124
Delivery brief summary
1 | Develop sprint 18 frontend story card
2 | Develop sprint 18 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W71
Timesheet |  | Date
Name | Role | Monday (May-4) |  | Tuesday (May-5) |  | Wednesday (May-6) |  | Thursday (May-7) |  | Friday (May-8) |  | Saturday (May-9) |  | Sunday (May-10)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Break | 0 | Break | 0 | Sprint 18 techinal development | 8 | Sprint 18 techinal development | 8 | Sprint 18 techinal development | 8 | Sprint 18 techinal development | 8 | Break | 0
Cao Xiaoqi | Dev | Break | 0 | Break | 0 | Sprint 18 techinal development | 8 | Sprint 18 techinal development | 8 | Sprint 18 techinal development | 8 | Sprint 18 techinal development | 8 | Break | 0
Liu Yue | QA | Break | 0 | Break | 0 | Sprint 18 techinal development | 8 | Sprint 18 techinal development | 8 | Sprint 18 techinal development | 8 | Sprint 18 techinal development | 8 | Break | 0
Huang Xinyu | BA | Break | 0 | Break | 0 | Sprint 18 business analysis | 8 | Sprint 18 business analysis | 8 | Break | 0 | Break | 0 | Break | 0 | Total working hours | 112
Delivery brief summary
1 | Develop sprint 18 frontend story card
2 | Develop sprint 18 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W72
Timesheet |  | Date
Name | Role | Monday (May-11) |  | Tuesday (May-12) |  | Wednesday (May-13) |  | Thursday (May-14) |  | Friday (May-15) |  | Saturday (May-16) |  | Sunday (May-17)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 19 techinal development | 8 | Sprint 19 techinal development | 8 | Sprint 19 techinal development | 8 | Sprint 19 techinal development | 8 | Sprint 19 techinal development | 8 | Break | 0 | Break | 0
Cao Xiaoqi | Dev | Sprint 19 techinal development | 8 | Sprint 19 techinal development | 8 | Sprint 19 techinal development | 8 | Sprint 19 techinal development | 8 | Sprint 19 techinal development | 4 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 19 techinal development | 8 | Sprint 19 techinal development | 8 | Sprint 19 techinal development | 8 | Sprint 19 techinal development | 8 | Sprint 19 techinal development | 8 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 19 business analysis | 8 | Sprint 19 business analysis | 8 | Sprint 19 business analysis | 8 | Sprint 19 business analysis | 8 | Sprint 19 business analysis | 8 | Break | 0 | Break | 0 | Total working hours | 156
Delivery brief summary
1 | Develop sprint 19 frontend story card
2 | Develop sprint 19 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W73
Timesheet |  | Date
Name | Role | Monday (May-18) |  | Tuesday (May-19) |  | Wednesday (May-20) |  | Thursday (May-21) |  | Friday (May-22) |  | Saturday (May-23) |  | Sunday (May-24)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 19 techinal development | 8 | Sprint 19 techinal development | 8 | Sprint 19 techinal development | 8 | Sprint 19 techinal development | 8 | Sprint 19 techinal development | 8 | Break | 0 | Break | 0
Cao Xiaoqi | Dev | Sprint 19 techinal development | 8 | Sprint 19 techinal development | 8 | Sprint 19 techinal development | 8 | Sprint 19 techinal development | 8 | Sprint 19 techinal development | 8 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 19 techinal development | 8 | Sprint 19 techinal development | 8 | Sprint 19 techinal development | 8 | Sprint 19 techinal development | 8 | Sprint 19 techinal development | 8 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 19 business analysis | 8 | Sprint 19 business analysis | 8 | Sprint 19 business analysis | 8 | Sprint 19 business analysis | 8 | Sprint 19 business analysis | 8 | Break | 0 | Break | 0 | Total working hours | 160
Delivery brief summary
1 | Develop sprint 19 frontend story card
2 | Develop sprint 19 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W74
Timesheet |  | Date
Name | Role | Monday (May-25) |  | Tuesday (May-26) |  | Wednesday (May-27) |  | Thursday (May-28) |  | Friday (May-29) |  | Saturday (May-30) |  | Sunday (May-31)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 20 techinal development | 8 | Sprint 20 techinal development | 8 | Sprint 20 techinal development | 8 | Sprint 20 techinal development | 8 | Sprint 20 techinal development | 8 | Break | 0 | Break | 0
Cao Xiaoqi | Dev | Sprint 20 techinal development | 8 | Sprint 20 techinal development | 8 | Sprint 20 techinal development | 8 | Sprint 20 techinal development | 8 | Sprint 20 techinal development | 8 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 20 techinal development | 8 | Sprint 20 techinal development | 8 | Sprint 20 techinal development | 8 | Sprint 20 techinal development | 8 | Break | 0 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 20 business analysis | 8 | Sprint 20 business analysis | 8 | Sprint 20 business analysis | 8 | Sprint 20 business analysis | 8 | Sprint 20 business analysis | 8 | Break | 0 | Break | 0 | Total working hours | 152
Delivery brief summary
1 | Develop sprint 20 frontend story card
2 | Develop sprint 20 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W75
Timesheet |  | Date
Name | Role | Monday (Jun-1) |  | Tuesday (Jun-2) |  | Wednesday (Jun-3) |  | Thursday (Jun-4) |  | Friday (Jun-5) |  | Saturday (Jun-6) |  | Sunday (Jun-7)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 20 techinal development | 8 | Sprint 20 techinal development | 8 | Sprint 20 techinal development | 8 | Sprint 20 techinal development | 8 | Sprint 20 techinal development | 8 | Break | 0 | Break | 0
Cao Xiaoqi | Dev | Sprint 20 techinal development | 8 | Sprint 20 techinal development | 8 | Sprint 20 techinal development | 8 | Sprint 20 techinal development | 8 | Sprint 20 techinal development | 8 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 20 techinal development | 8 | Sprint 20 techinal development | 8 | Sprint 20 techinal development | 8 | Sprint 20 techinal development | 8 | Sprint 20 techinal development | 8 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 20 business analysis | 8 | Sprint 20 business analysis | 8 | Sprint 20 business analysis | 8 | Sprint 20 business analysis | 8 | Sprint 20 business analysis | 8 | Break | 0 | Break | 0 | Total working hours | 160
Delivery brief summary
1 | Develop sprint 20 frontend story card
2 | Develop sprint 20 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W76
Timesheet |  | Date
Name | Role | Monday (Jun-8) |  | Tuesday (Jun-9) |  | Wednesday (Jun-10) |  | Thursday (Jun-11) |  | Friday (Jun-12) |  | Saturday (Jun-13) |  | Sunday (Jun-14)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 21 techinal development | 8 | Sprint 21 techinal development | 8 | Sprint 21 techinal development | 8 | Sprint 21 techinal development | 8 | Sprint 21 techinal development | 8 | Break | 0 | Break | 0
Cao Xiaoqi | Dev | Sprint 21 techinal development | 8 | Sprint 21 techinal development | 8 | Sprint 21 techinal development | 8 | Sprint 21 techinal development | 4 | Sprint 21 techinal development | 8 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 21 techinal development | 8 | Sprint 21 techinal development | 8 | Sprint 21 techinal development | 8 | Sprint 21 techinal development | 8 | Sprint 21 techinal development | 8 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 21 business analysis | 8 | Sprint 21 business analysis | 8 | Sprint 21 business analysis | 8 | Sprint 21 business analysis | 8 | Sprint 21 business analysis | 8 | Break | 0 | Break | 0 | Total working hours | 156
Delivery brief summary
1 | Develop sprint 21 frontend story card
2 | Develop sprint 21 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W77
Timesheet |  | Date
Name | Role | Monday (Jun-15) |  | Tuesday (Jun-16) |  | Wednesday (Jun-17) |  | Thursday (Jun-18) |  | Friday (Jun-19) |  | Saturday (Jun-20) |  | Sunday (Jun-21)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 21 techinal development | 8 | Sprint 21 techinal development | 8 | Sprint 21 techinal development | 8 | Sprint 21 techinal development | 8 | Sprint 21 techinal development | 8 | Break | 0 | Break | 0
Cao Xiaoqi | Dev | Sprint 21 techinal development | 8 | Sprint 21 techinal development | 8 | Sprint 21 techinal development | 8 | Sprint 21 techinal development | 8 | Sprint 21 techinal development | 8 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 21 techinal development | 8 | Sprint 21 techinal development | 8 | Sprint 21 techinal development | 8 | Sprint 21 techinal development | 8 | Sprint 21 techinal development | 8 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 21 business analysis | 8 | Sprint 21 business analysis | 8 | Sprint 21 business analysis | 8 | Sprint 21 business analysis | 8 | Sprint 21 business analysis | 8 | Break | 0 | Break | 0 | Total working hours | 160
Delivery brief summary
1 | Develop sprint 21 frontend story card
2 | Develop sprint 21 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W78
Timesheet |  | Date
Name | Role | Monday (Jun-22) |  | Tuesday (Jun-23) |  | Wednesday (Jun-24) |  | Thursday (Jun-25) |  | Friday (Jun-26) |  | Saturday (Jun-27) |  | Sunday (Jun-28)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 22 techinal development | 8 | Sprint 22 techinal development | 8 | Sprint 22 techinal development | 8 | Break | 0 | Break | 0 | Break | 0 | Sprint 22 techinal development | 8
Cao Xiaoqi | Dev | Sprint 22 techinal development | 8 | Sprint 22 techinal development | 8 | Sprint 22 techinal development | 8 | Break | 0 | Break | 0 | Break | 0 | Sprint 22 techinal development | 8
Liu Yue | QA | Sprint 22 techinal development | 8 | Sprint 22 techinal development | 8 | Sprint 22 techinal development | 8 | Break | 0 | Break | 0 | Break | 0 | Sprint 22 techinal development | 8
Huang Xinyu | BA | Sprint 22 business analysis | 8 | Sprint 22 business analysis | 8 | Sprint 22 business analysis | 8 | Break | 0 | Break | 0 | Break | 0 | Sprint 22 business analysis | 8 | Total working hours | 128
Delivery brief summary
1 | Develop sprint 22 frontend story card
2 | Develop sprint 22 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W79
Timesheet |  | Date
Name | Role | Monday (Jun-29) |  | Tuesday (Jun-30) |  | Wednesday (Jul-1) |  | Thursday (Jul-2) |  | Friday (Jul-3) |  | Saturday (Jul-4) |  | Sunday (Jul-5)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 22 techinal development | 8 | Sprint 22 techinal development | 8 | Sprint 22 techinal development | 8 | Sprint 22 techinal development | 8 | Sprint 22 techinal development | 8 | Break | 0 | Break | 0
Cao Xiaoqi | Dev | Sprint 22 techinal development | 8 | Sprint 22 techinal development | 8 | Sprint 22 techinal development | 8 | Sprint 22 techinal development | 8 | Sprint 22 techinal development | 8 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 22 techinal development | 8 | Sprint 22 techinal development | 8 | Sprint 22 techinal development | 8 | Sprint 22 techinal development | 8 | Sprint 22 techinal development | 8 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 22 business analysis | 8 | Sprint 22 business analysis | 8 | Sprint 22 business analysis | 8 | Sprint 22 business analysis | 8 | Break | 0 | Break | 0 | Break | 0 | Total working hours | 152
Delivery brief summary
1 | Develop sprint 22 frontend story card
2 | Develop sprint 22 backend story card
3 | Write api test script
4 | Analysis sprint tasks