## Summary
WEEK | Totol working hours | Total man-days
| 764 | 95.5
W32 | 60 | 7.5
W33 | 60 | 7.5
W34 | 60 | 7.5
W35 | 60 | 7.5
W36 | 140 | 17.5
W37 | 100 | 12.5
W38 | 140 | 17.5
W39 | 144 | 18

## W32
Timesheet |  | Date
Name | Role | Monday (Aug-05) |  | Tuesday (Aug-06) |  | Wednesday (Aug-07) |  | Thursday (Aug-08) |  | Friday (Aug-09) |  | Saturday (Aug-10) |  | Sunday (Aug-11)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 1 techinal development | 8 | Sprint 1 techinal development | 8 | Sprint 1 techinal development | 8 | Sprint 1 techinal development | 8 | Sprint 1 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 1 business analysis | 4 | Sprint 1 business analysis | 4 | Sprint 1 business analysis | 4 | Sprint 1 business analysis | 4 | Sprint 1 business analysis | 4 | Break | 0 | Break | 0 | Total working hours | 60
Delivery brief summary
1 | Prepare development environment
2 | Download project source code and be familiar with it
3 | sprint 1 stories develop
4 | Analysis sprint tasks

## W33
Timesheet |  | Date
Name | Role | Monday (Aug-12) |  | Tuesday (Aug-013) |  | Wednesday (Aug-14) |  | Thursday (Aug-15) |  | Friday (Aug-016) |  | Saturday (Aug-17) |  | Sunday (Aug-18)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 1 techinal development | 8 | Sprint 1 techinal development | 8 | Sprint 1 techinal development | 8 | Sprint 1 techinal development | 8 | Sprint 1 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 1 business analysis | 4 | Sprint 1 business analysis | 4 | Sprint 1 business analysis | 4 | Sprint 1 business analysis | 4 | Sprint 1 business analysis | 4 | Break | 0 | Break | 0 | Total working hours | 60
Delivery brief summary
1 | Develop sprint 1 story card
2 | fix image upload bug
3 | spike for refactor front-end
4 | Analysis sprint tasks

## W34
Timesheet |  | Date
Name | Role | Monday (Aug-19) |  | Tuesday (Aug-020) |  | Wednesday (Aug-21) |  | Thursday (Aug-22) |  | Friday (Aug-023) |  | Saturday (Aug-24) |  | Sunday (Aug-25)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 2 techinal development | 8 | Sprint 2 techinal development | 8 | Sprint 2 techinal development | 8 | Sprint 2 techinal development | 8 | Sprint 2 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 2 business analysis | 4 | Sprint 2 business analysis | 4 | Sprint 2 business analysis | 4 | Sprint 2 business analysis | 4 | Sprint 2 business analysis | 4 | Break | 0 | Break | 0 | Total working hours | 60
Delivery brief summary
1 | Develop sprint 2 story card
2 | fix sprint 2 bugs
3 | build frontend CI/CD with yueze
4 | Analysis sprint tasks

## w35
Timesheet |  | Date
Name | Role | Monday (Aug-26) |  | Tuesday (Aug-27) |  | Wednesday (Aug-28) |  | Thursday (Aug-29) |  | Friday (Aug-30) |  | Saturday (Aug-31) |  | Sunday (Sep-01)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 2 techinal development | 8 | Sprint 2 techinal development | 8 | Sprint 2 techinal development | 8 | Sprint 2 techinal development | 8 | Sprint 2 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 2 business analysis | 4 | Sprint 2 business analysis | 4 | Sprint 2 business analysis | 4 | Sprint 2 business analysis | 4 | Sprint 2 business analysis | 4 | Break | 0 | Break | 0 | Total working hours | 60
Delivery brief summary
1 | Develop sprint 2 story card
2 | modify UI buttons color
3 | build frontend CI/CD with yueze
4 | Analysis sprint tasks

## W36
Timesheet |  | Date
Name | Role | Monday (Sep-02) |  | Tuesday (Sep-03) |  | Wednesday (Sep-04) |  | Thursday (Sep-05) |  | Friday (Sep-06) |  | Saturday (Sep-07) |  | Sunday (Sep-08)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 3 business analysis | 4 | Sprint 3 business analysis | 4 | Sprint 3 business analysis | 4 | Sprint 3 business analysis | 4 | Sprint 3 business analysis | 4 | Break | 0 | Break | 0
Cao Xiaoqi | DEV | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Break | 0 | Break | 0
Chen Pei | QA | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Break | 0 | Break | 0 | Total working hours | 140
Delivery brief summary
1 | Develop sprint 3 story card
2 | Prepare backend develop environment
3 | Build QA environment
4 | Analysis sprint tasks

## W37
Timesheet |  | Date
Name | Role | Monday (Sep-09) |  | Tuesday (Sep-10) |  | Wednesday (Sep-11) |  | Thursday (Sep-12) |  | Friday (Sep-13) |  | Saturday (Sep-14) |  | Sunday (Sep-15)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 4 | Sprint 3 techinal development | 0 | Sprint 3 techinal development | 0 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 3 business analysis | 4 | Sprint 3 business analysis | 4 | Sprint 3 business analysis | 4 | Sprint 3 business analysis | 4 | Sprint 3 business analysis | 0 | Break | 0 | Break | 0
Cao Xiaoqi | DEV | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 0 | Break | 0 | Break | 0
Chen Pei | QA | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 8 | Sprint 3 techinal development | 0 | Break | 0 | Break | 0 | Total working hours | 100
Delivery brief summary
1 | Develop sprint 3 frontend story card
2 | Develop sprint 3 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W38
Timesheet |  | Date
Name | Role | Monday (Sep-16) |  | Tuesday (Sep-17) |  | Wednesday (Sep-18) |  | Thursday (Sep-19) |  | Friday (Sep-20) |  | Saturday (Sep-21) |  | Sunday (Sep-22)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 4 business analysis | 4 | Sprint 4 business analysis | 4 | Sprint 4 business analysis | 4 | Sprint 4 business analysis | 4 | Sprint 4 business analysis | 4 | Break | 0 | Break | 0
Cao Xiaoqi | DEV | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Break | 0 | Break | 0
Chen Pei | QA | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Break | 0 | Break | 0 | Total working hours | 140
Delivery brief summary
1 | Develop sprint 4 frontend story card
2 | Develop sprint 4 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W39
Timesheet |  | Date
Name | Role | Monday (Sep-23) |  | Tuesday (Sep-24) |  | Wednesday (Sep-25) |  | Thursday (Sep-26) |  | Friday (Sep-27) |  | Saturday (Sep-28) |  | Sunday (Sep-29)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Break | 0 | Sprint 4 techinal development | 8
Wang Dongxue | BA | Sprint 4 business analysis | 4 | Sprint 4 business analysis | 0 | Sprint 4 business analysis | 4 | Sprint 4 business analysis | 0 | Sprint 4 business analysis | 0 | Break | 0 | Break | 0
Cao Xiaoqi | DEV | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Break | 0 | Break | 0
Chen Pei | QA | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Sprint 4 techinal development | 8 | Break | 0 | Sprint 4 techinal development | 8 | Total working hours | 144
Delivery brief summary
1 | Develop sprint 4 frontend story card
2 | Develop sprint 4 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W40
Timesheet |  | Date
Name | Role | Monday (Sep-30) |  | Tuesday (Oct-01) |  | Wednesday (Oct-02) |  | Thursday (Oct-03) |  | Friday (Oct-04) |  | Saturday (Oct-05) |  | Sunday (Oct-06)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 4 techinal development | 8 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 4 business analysis | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0
Cao Xiaoqi | DEV | Sprint 4 techinal development | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0
Chen Pei | QA | Sprint 4 techinal development | 8 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Total working hours | 16
Delivery brief summary
1 | Develop sprint 4 frontend story card
2 | Develop sprint 4 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W41
Timesheet |  | Date
Name | Role | Monday (Oct-7) |  | Tuesday (Oct-8) |  | Wednesday (Oct-9) |  | Thursday (Oct-10) |  | Friday (Oct-11) |  | Saturday (Oct-12) |  | Sunday (Oct-13)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Break | 0 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Break | 0
Wang Dongxue | BA | Break | 0 | Sprint 5 business analysis | 4 | Sprint 5 business analysis | 4 | Sprint 5 business analysis | 4 | Sprint 5 business analysis | 4 | Break | 0 | Break | 0
Cao Xiaoqi | DEV | Break | 0 | Break | 0 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Break | 0
Chen Pei | QA | Break | 0 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Break | 0 | Total working hours | 128
Delivery brief summary
1 | Develop sprint 5 frontend story card
2 | Develop sprint 5 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W42
Timesheet |  | Date
Name | Role | Monday (Oct-14) |  | Tuesday (Oct-15) |  | Wednesday (Oct-16) |  | Thursday (Oct-17) |  | Friday (Oct-18) |  | Saturday (Oct-19) |  | Sunday (Oct-20)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 5 business analysis | 4 | Sprint 5 business analysis | 4 | Sprint 5 business analysis | 4 | Sprint 5 business analysis | 4 | Sprint 5 business analysis | 4 | Break | 0 | Break | 0
Cao Xiaoqi | DEV | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Break | 0 | Break | 0
Chen Pei | QA | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Break | 0 | Break | 0 | Total working hours | 140
Delivery brief summary
1 | Develop sprint 5 frontend story card
2 | Develop sprint 5 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W43
Timesheet |  | Date
Name | Role | Monday (Oct-21) |  | Tuesday (Oct-22) |  | Wednesday (Oct-23) |  | Thursday (Oct-24) |  | Friday (Oct-25) |  | Saturday (Oct-26) |  | Sunday (Oct-27)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 5 techinal development | 4 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 5 business analysis | 4 | Sprint 5 business analysis | 4 | Sprint 5 business analysis | 4 | Sprint 5 business analysis | 4 | Sprint 5 business analysis | 4 | Break | 0 | Break | 0
Cao Xiaoqi | DEV | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Break | 0 | Break | 0
Chen Pei | QA | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Sprint 5 techinal development | 8 | Break | 0 | Break | 0 | Total working hours | 176
Delivery brief summary
1 | Develop sprint 5 frontend story card
2 | Develop sprint 5 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W44
Timesheet |  | Date
Name | Role | Monday (Oct-28) |  | Tuesday (Oct-29) |  | Wednesday (Oct-30) |  | Thursday (Oct-31) |  | Friday (Nov-1) |  | Saturday (Nov-2) |  | Sunday (Nov-3)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 6 business analysis | 4 | Break | 0 | Sprint 6 business analysis | 4 | Sprint 6 business analysis | 4 | Sprint 6 business analysis | 4 | Break | 0 | Break | 0
Cao Xiaoqi | DEV | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 4 | Break | 0
Liu Yue | QA | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Break | 0 | Break | 0 | Total working hours | 140
Delivery brief summary
1 | Develop sprint 6 frontend story card
2 | Develop sprint 6 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W45
Timesheet |  | Date
Name | Role | Monday (Nov-4) |  | Tuesday (Nov-5) |  | Wednesday (Nov-6) |  | Thursday (Nov-7) |  | Friday (Nov-8) |  | Saturday (Nov-9) |  | Sunday (Nov-10)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 16 | Sprint 6 techinal development | 4 | Break | 0
Wang Dongxue | BA | Sprint 6 business analysis | 4 | Sprint 6 business analysis | 4 | Sprint 6 business analysis | 4 | Sprint 6 business analysis | 4 | Sprint 6 business analysis | 4 | Break | 0 | Break | 0
Cao Xiaoqi | DEV | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 4 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 16 | Sprint 6 techinal development | 4 | Break | 0
Liu Yue | QA | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Sprint 6 techinal development | 8 | Break | 0 | Break | 0 | Total working hours | 160
Delivery brief summary
1 | Develop sprint 6 frontend story card
2 | Develop sprint 6 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W46
Timesheet |  | Date
Name | Role | Monday (Nov-11) |  | Tuesday (Nov-12) |  | Wednesday (Nov-13) |  | Thursday (Nov-14) |  | Friday (Nov-15) |  | Saturday (Nov-16) |  | Sunday (Nov-17)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 7 business analysis | 4 | Sprint 7 business analysis | 4 | Sprint 7 business analysis | 4 | Sprint 7 business analysis | 2 | Break | 0 | Break | 0 | Break | 0
Cao Xiaoqi | DEV | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Break | 0 | Sprint 7 techinal development | 8 | Break | 0 | Break | 0 | Total working hours | 126
Delivery brief summary
1 | Develop sprint 7 frontend story card
2 | Develop sprint 7 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W47
Timesheet |  | Date
Name | Role | Monday (Nov-18) |  | Tuesday (Nov-19) |  | Wednesday (Nov-20) |  | Thursday (Nov-21) |  | Friday (Nov-22) |  | Saturday (Nov-23) |  | Sunday (Nov-24)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Break | 0 | Sprint 7 business analysis | 2 | Sprint 7 business analysis | 4 | Sprint 7 business analysis | 4 | Sprint 7 business analysis | 4 | Break | 0 | Break | 0
Cao Xiaoqi | DEV | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 8 | Sprint 7 techinal development | 4 | Break | 0 | Total working hours | 138
Delivery brief summary
1 | Develop sprint 7 frontend story card
2 | Develop sprint 7 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W48
Timesheet |  | Date
Name | Role | Monday (Nov-25) |  | Tuesday (Nov-26) |  | Wednesday (Nov-27) |  | Thursday (Nov-28) |  | Friday (Nov-29) |  | Saturday (Nov-30) |  | Sunday (Dec-1)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 8 business analysis | 4 | Sprint 8 business analysis | 4 | Break | 0 | Break | 0 | Sprint 8 business analysis | 4 | Break | 0 | Break | 0
Cao Xiaoqi | DEV | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Break | 0 | Break | 0 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 8 business analysis | 8 | Sprint 8 business analysis | 8 | Sprint 8 business analysis | 8 | Sprint 8 business analysis | 8 | Break | 0 | Break | 0 | Break | 0 | Total working hours | 148
Delivery brief summary
1 | Develop sprint 8 frontend story card
2 | Develop sprint 8 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W49
Timesheet |  | Date
Name | Role | Monday (Dec-2) |  | Tuesday (Dec-3) |  | Wednesday (Dec-4) |  | Thursday (Dec-5) |  | Friday (Dec-6) |  | Saturday (Dec-7) |  | Sunday (Dec-8)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI DEV | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 8 business analysis | 4 | Sprint 8 business analysis | 4 | Sprint 8 business analysis | 4 | Sprint 8 business analysis | 2 | Sprint 8 business analysis | 4 | Break | 0 | Break | 0
Cao Xiaoqi | DEV | Break | 0 | Break | 0 | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Sprint 8 techinal development | 8 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 8 business analysis | 8 | Sprint 8 business analysis | 8 | Sprint 8 business analysis | 8 | Sprint 8 business analysis | 8 | Sprint 8 business analysis | 8 | Break | 0 | Break | 0 | Total working hours | 162
Delivery brief summary
1 | Develop sprint 8 frontend story card
2 | Develop sprint 8 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W50
Timesheet |  | Date
Name | Role | Monday (Dec-9) |  | Tuesday (Dec-10) |  | Wednesday (Dec-11) |  | Thursday (Dec-12) |  | Friday (Dec-13) |  | Saturday (Dec-14) |  | Sunday (Dec-15)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Break | 0 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 9 business analysis | 4 | Sprint 9 business analysis | 4 | Sprint 9 business analysis | 4 | Sprint 9 business analysis | 4 | Sprint 9 business analysis | 4 | Break | 0 | Break | 0
Cao Xiaoqi | Dev | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Break | 0 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Break | 0 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 9 business analysis | 8 | Sprint 9 business analysis | 8 | Sprint 9 business analysis | 8 | Sprint 9 business analysis | 8 | Sprint 9 business analysis | 8 | Break | 0 | Break | 0 | Total working hours | 156
Delivery brief summary
1 | Develop sprint 9 frontend story card
2 | Develop sprint 9 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W51
Timesheet |  | Date
Name | Role | Monday (Dec-16) |  | Tuesday (Dec-17) |  | Wednesday (Dec-18) |  | Thursday (Dec-19) |  | Friday (Dec-20) |  | Saturday (Dec-21) |  | Sunday (Dec-22)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 9 business analysis | 4 | Sprint 9 business analysis | 4 | Sprint 9 business analysis | 4 | Break | 0 | Sprint 9 business analysis | 4 | Break | 0 | Break | 0
Cao Xiaoqi | Dev | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Sprint 9 techinal development | 8 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 9 business analysis | 8 | Sprint 9 business analysis | 8 | Sprint 9 business analysis | 8 | Sprint 9 business analysis | 8 | Sprint 9 business analysis | 8 | Break | 0 | Break | 0 | Total working hours | 176
Delivery brief summary
1 | Develop sprint 9 frontend story card
2 | Develop sprint 9 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W52
Timesheet |  | Date
Name | Role | Monday (Dec-23) |  | Tuesday (Dec-24) |  | Wednesday (Dec-25) |  | Thursday (Dec-26) |  | Friday (Dec-27) |  | Saturday (Dec-28) |  | Sunday (Dec-29)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 10 techinal development | 8 | Sprint 10 techinal development | 8 | Sprint 10 techinal development | 8 | Sprint 10 techinal development | 8 | Sprint 10 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 10 business analysis | 4 | Sprint 10 business analysis | 4 | Sprint 10 business analysis | 4 | Sprint 10 business analysis | 4 | Break | 0 | Break | 0 | Break | 0
Cao Xiaoqi | Dev | Sprint 10 techinal development | 8 | Sprint 10 techinal development | 8 | Sprint 10 techinal development | 8 | Sprint 10 techinal development | 8 | Sprint 10 techinal development | 8 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 10 techinal development | 8 | Break | 0 | Sprint 10 techinal development | 8 | Sprint 10 techinal development | 8 | Sprint 10 techinal development | 8 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 10 business analysis | 8 | Sprint 10 business analysis | 8 | Sprint 10 business analysis | 8 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Total working hours | 152
Delivery brief summary
1 | Develop sprint 10 frontend story card
2 | Develop sprint 10 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W53
Timesheet |  | Date
Name | Role | Monday (Dec-30) |  | Tuesday (Dec-31) |  | Wednesday (Jan-1) |  | Thursday (Jan-2) |  | Friday (Jan-3) |  | Saturday (Jan-4) |  | Sunday (Jan-5)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 10 techinal development | 8 | Sprint 10 techinal development | 8 | Break | 0 | Sprint 10 techinal development | 8 | Sprint 10 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Break | 0 | Break | 0 | Break | 0 | Sprint 10 business analysis | 4 | Sprint 10 business analysis | 4 | Break | 0 | Break | 0
Cao Xiaoqi | Dev | Sprint 10 techinal development | 8 | Sprint 10 techinal development | 8 | Break | 0 | Sprint 10 techinal development | 8 | Sprint 10 techinal development | 4 | Break | 0 | Break | 0
Liu Yue | QA | Break | 0 | Break | 0 | Break | 0 | Sprint 10 techinal development | 8 | Sprint 10 techinal development | 8 | Break | 0 | Break | 0
Huang Xinyu | BA | Break | 0 | Break | 0 | Break | 0 | Sprint 10 business analysis | 8 | Sprint 10 business analysis | 8 | Break | 0 | Break | 0 | Total working hours | 100
Delivery brief summary
1 | Develop sprint 10 frontend story card
2 | Develop sprint 10 backend story card
3 | Write api test script
4 | Analysis sprint tasks

## W54
Timesheet |  | Date
Name | Role | Monday (Jan-6) |  | Tuesday (Jan-7) |  | Wednesday (Jan-8) |  | Thursday (Jan-9) |  | Friday (Jan-10) |  | Saturday (Jan-11) |  | Sunday (Jan-12)
|  | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours | Workload Brief | Hours
Ren Zhitong | UI Dev | Sprint 11 techinal development | 8 | Sprint 11 techinal development | 8 | Sprint 11 techinal development | 8 | Sprint 11 techinal development | 8 | Sprint 11 techinal development | 8 | Break | 0 | Break | 0
Wang Dongxue | BA | Sprint 11 business analysis | 4 | Sprint 11 business analysis | 2 | Sprint 11 business analysis | 4 | Sprint 11 business analysis | 4 | Sprint 11 business analysis | 4 | Break | 0 | Break | 0
Cao Xiaoqi | Dev | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0 | Break | 0
Liu Yue | QA | Sprint 11 techinal development | 8 | Sprint 11 techinal development | 8 | Sprint 11 techinal development | 8 | Sprint 11 techinal development | 8 | Sprint 11 techinal development | 8 | Break | 0 | Break | 0
Huang Xinyu | BA | Sprint 11 business analysis | 8 | Sprint 11 business analysis | 8 | Sprint 11 business analysis | 8 | Sprint 11 business analysis | 8 | Sprint 11 business analysis | 8 | Break | 0 | Break | 0 | Total working hours | 138
Delivery brief summary
1 | Develop sprint 11 frontend story card
2 | Develop sprint 11 backend story card
3 | Write api test script
4 | Analysis sprint tasks